TroMate

Software Development Plan

Version 1.0

Revision History

| Date | Version | Description | Author |
| --- | --- | --- | --- |
| 16/Oct/26 | 1.0 | Initial Software Development Plan for the TroMate MVP, based on PA0 course schedule, MVP Scope Decision Record, Team Roles and Jira SOP. | Hào Nguyễn Gia |

Table of Contents

1.	Introduction	3

2.	Project Overview	4

2.1	Project Purpose, Scope, and Objectives	4

2.2	Assumptions and Constraints	4

2.3	Project Deliverables	5

3.	Project Organization	5

3.1	Organizational Structure	5

3.2	Roles and Responsibilities	6

4.	Management Process	7

4.1	Project Estimates	7

4.2	Project Plan	8

4.2.1	Phase and Iteration Plan	8

4.2.2	Releases	11

4.2.3	Project Schedule	11

4.2.4	Project Resourcing	12

4.3	Project Monitoring and Control	12

4.3.1	Reporting	12

4.3.2	Risk Management	13

4.3.3	Configuration Management	14

Software Development Plan

Introduction

This Software Development Plan (SDP) describes how the TroMate team will plan, organize, execute and control the development of TroMate, a Telegram-based shared-expense assistant for students and young professionals who rent rooms together. The plan covers the 10-week course project from 05/Oct/2026 to 13/Dec/2026 and follows the course's combined RUP and Scrum process: the RUP Inception, Elaboration and Construction phases are mapped onto five two-week Scrum sprints.

This plan is derived from, and should be read together with, the following project documents:

- PA0 – Group Registration & Tools Setup (course schedule, mandatory tools and repository structure).

- TroMate Project Decision Record & Detailed Feature Specification (MVP scope, target users and technical assumptions).

- Team Roles and Responsibilities.

- Jira Working Rules & Standard Operating Procedures (SOP).

Section 2 summarizes the project's purpose, scope, assumptions and deliverables. Section 3 describes the team organization and responsibilities. Section 4 defines the management process: estimates, the phase and sprint plan, releases, schedule, resourcing, reporting, risk management and configuration management.

Project Overview

Project Purpose, Scope, and Objectives

Purpose. Roommates sharing rented rooms in cities such as Ho Chi Minh City and Hanoi (typically 2–5 people aged 18–26) make many small shared purchases and split monthly rent and utility bills. Today they log these by hand in Excel or Splitwise after paying, calculate shares manually, and have to ask each other for money directly, which is awkward. TroMate removes this friction inside the room's existing Telegram group: members log an expense by typing a natural-language message or sending a photo of a receipt, bill or meter; the bot calculates each person's share, simplifies debts, and helps members settle with a pre-filled VietQR code and polite automated reminders.

Scope. The MVP delivers the following features:

- Natural-language expense parsing in Vietnamese, including informal currency tokens (k, kđ, tr, xị, củ, ngàn).

- Receipt and rent-bill OCR parsing, including combined photo + text input.

- Electricity and water meter scanner and rent invoice breakdown.

- Confirmation protocol and transaction state machine (PENDING, confirmed, rejected) with per-group concurrency locks.

- Debt simplification engine (minimum cash flow).

- Dynamic VietQR settlement generation with Confirm Paid / Confirm Received flow.

- Group expense summary (/balance) with real-time net balances.

- Polite automated debt reminders with a 1-tap VietQR payment button.

- Telegram Mini App showing balances, transaction history and room configuration.

Deferred to a later release: usage anomaly detector, monthly expense breakdown and meme-based reminder images. Out of scope: shared room fund ledger, chore and trash scheduler, and move-in asset and deposit checklist.

Objectives.

- Release a working MVP (v1.0) of the TroMate Telegram bot and Mini App by 13/Dec/2026 (end of Sprint 5, PA5).

- Let members log a shared expense from a text message or a photo without any manual spreadsheet entry.

- Ensure no transaction affects official balances until it is explicitly confirmed by the members involved.

- Reduce settlement to the minimum number of transfers and allow 1-tap payment through VietQR.

- Practise professional teamwork with Jira, GitHub and Slack, following the team's Jira SOP and Definition of Done.

- Submit every course assignment (PA0–PA5) on or before its deadline.

Assumptions and Constraints

- Fixed schedule: 10 weeks (05/Oct/2026 – 13/Dec/2026), organized as 5 Scrum sprints of 2 weeks each. Assignment deadlines (PA0–PA5) are fixed by the course.

- Fixed team: 5 members; no members will be added during the project. Each member is assumed to contribute about 10 hours per week alongside other courses.

- Zero budget: only free tools and free service tiers are used (Telegram Bot API, Google Cloud Vision free quota or Tesseract, free hosting, Redis and PostgreSQL free tiers).

- Platform: Telegram Bot API + Telegram Mini App (Webview). No native mobile application is built.

- Technology: FastAPI / Node.js backend, Redis for transient state locks, PostgreSQL for the immutable ledger, and a background scheduler (Celery / Redis Queue / APScheduler) for reminders.

- Payments: settlement uses VietQR codes following the EMVCo / Napas standards. TroMate does not move money or integrate with bank APIs; payments are confirmed manually by members.

- OCR quality: accuracy depends on photo quality, so extracted values are always shown for confirmation and editing before they are committed.

- Mandatory tools (PA0): Moodle, the class Facebook group, Slack, Jira and GitHub with the required folder structure.

- Users: real-user testing is limited to pilot room groups recruited by the team, including the potential users interviewed for PA0.

Project Deliverables

The artifacts below are stored in the GitHub repository (/docs and /pa) and submitted to Moodle with the corresponding assignment.

| No. | Deliverable | Owner | Sprint / PA | Target date |
| --- | --- | --- | --- | --- |
| 1 | Group registration, project proposal and evidence of ≥5 user interviews | Scrum Master (all) | S1 / PA0 | 11/Oct/2026 |
| 2 | Tools setup: Slack channel, Jira board, GitHub repository (/src, /docs, /pa) | Scrum Master, Tech Lead | S1 / PA0 | 11/Oct/2026 |
| 3 | MVP Scope Decision Record, Team Roles, Jira SOP | Product Owner, Scrum Master | S1 / PA1 | 18/Oct/2026 |
| 4 | Vision Document | Product Owner / BA | S1 / PA1 | 18/Oct/2026 |
| 5 | Software Development Plan (this document) | Scrum Master | S1 / PA1 | 18/Oct/2026 |
| 6 | Software Requirements Specification (use cases, user stories with acceptance criteria) | Product Owner / BA | Baseline S1 / PA1; final S2 / PA2 | 18/Oct – 01/Nov/2026 |
| 7 | UI prototype (wireframes, chat flows, Mini App screens) | UI/UX Designer | Baseline S1 / PA1; final S2 / PA2 | 18/Oct – 01/Nov/2026 |
| 8 | Initial architecture and technical spike reports (OCR, VietQR, Mini App) | Technical Lead | S2 / PA2 | 01/Nov/2026 |
| 9 | Software Architecture Document, UML models, detailed UI design | Technical Lead, UI/UX Designer | S3 / PA3 | 15/Nov/2026 |
| 10 | Test Plan | QA / Tester | S3 / PA3 | 15/Nov/2026 |
| 11 | Working software v0.1 (text logging → confirmation → ledger) | Technical Lead (dev team) | S3 / PA3 | 15/Nov/2026 |
| 12 | Beta v0.5, test cases and sprint test report | Technical Lead, QA | S4 / PA4 | 29/Nov/2026 |
| 13 | MVP v1.0 (bot + Mini App), release notes, user guide | Whole team | S5 / PA5 | 13/Dec/2026 |
| 14 | Final test report and final demo / presentation | QA, whole team | S5 / PA5 | 13/Dec/2026 |
| 15 | Sprint reports, weekly status reports and retrospective notes | Scrum Master | Every sprint | End of each sprint |

Project Organization

Organizational Structure

TroMate is developed by a single five-person Scrum team. The Product Owner owns the product backlog and business decisions. The Scrum Master / Project Lead owns the process, the Jira board and this plan. The Technical Lead, UI/UX Designer and QA / Tester form the development team and are jointly responsible for delivering a Done increment every sprint.

The course instructor and TAs are the external review authority: they approve the project proposal and evaluate each PA submission. Pilot users (roommate groups) are stakeholders who give feedback through interviews, prototype reviews and the beta.

Figure 1. TroMate project organization

Decision authority: business and scope decisions – Product Owner; technical decisions – Technical Lead; process, schedule and due-date changes – Scrum Master together with the Technical Lead. Decisions are recorded in Jira or the repository.

Roles and Responsibilities

| Person | Role | Responsibilities |
| --- | --- | --- |
| Kiệt Trịnh Võ Nam | Scrum Master / Project Lead | Organize Sprint Planning, Daily Scrum, Sprint Review and Retrospective. Maintain the Jira board; track sprint progress and deadlines. Remove blockers and coordinate collaboration across the team. Enforce the agreed workflow and Definition of Done. Keep project plans and management documents up to date. |
| Tôn Huỳnh Chí | Product Owner / Business Analyst | Collect and clarify user needs and product requirements. Define the MVP scope and prioritize the Product Backlog. Write and review user stories and acceptance criteria. Resolve business questions during design, development and testing. Review delivered features against acceptance criteria. |
| Hào Nguyễn Gia | Technical Lead | Define the architecture, technology stack and coding standards. Assess technical feasibility, dependencies and risks. Break down technical work and support effort estimation. Review code and support implementation and integration. Coordinate with QA to investigate and resolve defects. |
| Nam Phạm Hữu | UI/UX Designer | Translate requirements into user flows and wireframes. Design consistent, accessible screens and reusable components. Cover loading, empty, error and success states. Create prototypes and refine them with usability feedback. Provide approved designs and assets for implementation. |
| Hưng Cao Quảng | QA / Tester | Plan testing and write test cases from acceptance criteria. Test expense recording, balance calculation, settlement and error handling. Report reproducible bugs in Jira with expected and actual results. Retest fixes and run regression before demos and releases. Report unresolved risks; verify testing requirements in the DoD. |

Responsibility for each discipline and supporting process:

| Discipline / supporting process | Responsible | Supporting |
| --- | --- | --- |
| Project management (planning, sprint ceremonies, Jira, reports) | Scrum Master | All members |
| Requirements (interviews, Vision, SRS, user stories, acceptance criteria) | Product Owner / BA | UI/UX Designer, QA |
| Analysis & design (architecture, data model, UML) | Technical Lead | Product Owner |
| UI/UX design and prototype | UI/UX Designer | Product Owner, Technical Lead |
| Implementation (bot backend, OCR, debt engine, VietQR, Mini App) | Technical Lead (coordinates) | All members implement backlog items |
| Testing and quality assurance | QA / Tester | Technical Lead; Product Owner for acceptance |
| Configuration & change management (GitHub, branches, releases) | Technical Lead | Scrum Master |
| Deployment and environments | Technical Lead | QA / Tester |

Each member is primarily responsible for the assigned role but supports the rest of the team. The UI/UX Designer coordinates with the Product Owner and Technical Lead before finalizing designs, and QA is involved early in requirements and design discussions. Every member keeps their Jira issues up to date.

Management Process

Project Estimates

Cost. This is a zero-budget project. All tools (Jira, GitHub, Slack, Telegram Bot API) and infrastructure (OCR, hosting, Redis, PostgreSQL) use free plans or free quotas.

Effort. Capacity is 5 members × about 10 hours/week × 10 weeks ≈ 500 person-hours, distributed by discipline as follows:

| Discipline | Share | Estimated effort (person-hours) |
| --- | --- | --- |
| Project management | 10% | 50 |
| Requirements | 12% | 60 |
| Analysis & design (incl. UI/UX) | 15% | 75 |
| Implementation | 38% | 190 |
| Testing | 17% | 85 |
| Deployment & documentation | 8% | 40 |
| Total | 100% | 500 |

Product backlog estimate. MVP epics are estimated in story points (SP) with Planning Poker (Fibonacci scale):

| MVP epic | Priority | Story points | Planned sprint |
| --- | --- | --- | --- |
| Infrastructure: bot skeleton, Telegram webhook, CI pipeline, DB setup | High | 5 | Sprint 2 |
| Natural-language expense parsing & currency normalization | High | 8 | Sprint 3 |
| Confirmation protocol, state machine & concurrency control | High | 13 | Sprint 3 |
| Receipt & rent-bill OCR + multimodal input | High | 13 | Sprint 4 |
| Debt simplification engine | High | 5 | Sprint 4 |
| Dynamic VietQR & settlement confirmation | High | 8 | Sprint 4 |
| Group summary (/balance) | High | 3 | Sprint 4 |
| Meter scanner & rent invoice breakdown | Medium | 8 | Sprint 5 |
| Polite automated debt reminder | High | 5 | Sprint 5 |
| Telegram Mini App (balances, history, room config) | Medium | 13 | Sprint 5 |
| Total |  | 81 |  |

Basis of estimates: whole-team Planning Poker, technical breakdown by the Technical Lead, and the PO's priorities from the MVP Scope Decision Record. The plan assumes a development velocity of about 21–29 SP per sprint in Sprints 3–5.

Re-estimation happens at every Sprint Planning; after the Sprint 2 technical spikes (OCR, VietQR, Telegram Mini App); whenever the Product Owner approves a scope change; and whenever actual velocity deviates noticeably from the plan. As defined in the Jira SOP, due dates are never changed without approval from the Scrum Master / Technical Lead.

Project Plan

The project follows the course schedule defined in PA0: RUP phases are mapped onto five two-week Scrum sprints. Each sprint starts on a Monday with Sprint Planning and ends on a Sunday with the Sprint Review, Retrospective and PA submission.

Phase and Iteration Plan

Phases

| Phase (RUP) | Sprints | Start | End | Objectives | Milestone |
| --- | --- | --- | --- | --- | --- |
| Inception | Sprint 1 | 05/Oct/2026 | 18/Oct/2026 | Form the team and set up tools; validate the problem with ≥5 user interviews; agree on the vision, MVP scope and plan. | M1 – Lifecycle Objectives (PA1) |
| Elaboration | Sprints 2–3 | 19/Oct/2026 | 15/Nov/2026 | Complete requirements; define and validate the architecture; retire technical risks (OCR, VietQR, concurrency); detailed design and test plan; first working software. | M2 – Lifecycle Architecture (PA3, v0.1) |
| Construction | Sprints 4–5 | 16/Nov/2026 | 13/Dec/2026 | Implement and test the remaining MVP features; run the beta pilot; stabilize and release the MVP. | M3 – Initial Operational Capability (PA5, v1.0) |

A full Transition phase (production rollout beyond pilot users) falls outside the 10-week course. The pilot, user guide and release activities in Sprint 5 cover the transition work needed for the MVP.

Iterations (sprints)

| Sprint | Dates | Assignment | Sprint goal | Main objectives / backlog items |
| --- | --- | --- | --- | --- |
| Sprint 1 (Inception) | 05/Oct – 18/Oct/2026 | PA0 (11/Oct), PA1 (18/Oct) | Project defined and team set up | Group registration and project proposal ≥5 user interviews with evidence Slack, Jira, GitHub setup MVP scope decision, team roles, Jira SOP Vision document and SDP SRS and UI prototype baselines |
| Sprint 2 (Elaboration) | 19/Oct – 01/Nov/2026 | PA2 (01/Nov) | Requirements complete; initial design agreed | Use-case model, user stories and AC for all MVP epics Clickable UI prototype (chat flows, Mini App) Initial architecture (webhook, backend, Redis, PostgreSQL) Spikes: OCR engine comparison, VietQR payload, Mini App auth Bot skeleton, CI pipeline, DB setup (5 SP) |
| Sprint 3 (Elaboration) | 02/Nov – 15/Nov/2026 | PA3 (15/Nov) | First working software: log an expense by text and confirm it | Software Architecture Document, UML, DB schema Test Plan NL parsing + currency normalization (8 SP) Confirmation protocol, state machine, Redis group lock (13 SP) Release v0.1 |
| Sprint 4 (Construction) | 16/Nov – 29/Nov/2026 | PA4 (29/Nov) | Log expenses from photos and settle debts | Receipt/bill OCR + multimodal input (13 SP) Debt simplification engine (5 SP) VietQR + settlement confirmation (8 SP) /balance summary (3 SP) Test cases, regression; Beta v0.5 to pilot rooms |
| Sprint 5 (Construction) | 30/Nov – 13/Dec/2026 | PA5 (13/Dec) | MVP complete and released | Meter scanner & rent breakdown (8 SP) Polite automated reminders (5 SP) Telegram Mini App (13 SP) Pilot feedback fixes, full regression User guide, release notes, final demo; v1.0 |

Work Breakdown Structure (WBS)

| WBS ID | Work package | Owner |
| --- | --- | --- |
| 1 | Project management – planning, sprint ceremonies, Jira tracking, status reports | Scrum Master |
| 2 | Requirements – interviews, Vision, SRS, user stories and acceptance criteria | Product Owner / BA |
| 3.1 | Analysis & design – architecture, data model, UML, technical spikes | Technical Lead |
| 3.2 | UI/UX – user flows, wireframes, prototype, Mini App design | UI/UX Designer |
| 4.1 | Implementation – bot infrastructure, webhook, CI/CD | Technical Lead |
| 4.2 | Implementation – natural-language parsing & currency normalization | Development team |
| 4.3 | Implementation – OCR: receipts, rent bills, meters | Development team |
| 4.4 | Implementation – transaction state machine & concurrency control | Development team |
| 4.5 | Implementation – debt simplification engine & /balance | Development team |
| 4.6 | Implementation – VietQR generation & settlement flow | Development team |
| 4.7 | Implementation – reminder scheduler | Development team |
| 4.8 | Implementation – Telegram Mini App | Development team, UI/UX Designer |
| 5 | Testing – test plan, test cases, functional, regression and pilot/UAT testing | QA / Tester |
| 6 | Deployment & release – environments, releases, release notes, user guide | Technical Lead |

Major milestones

| Milestone | Date | Achievement criteria |
| --- | --- | --- |
| PA0 – Group registration & tools setup | 11/Oct/2026 | Group registered; proposal with evidence of ≥5 interviews approved by TAs; Slack, Jira and GitHub set up. |
| M1 – Lifecycle Objectives (PA1) | 18/Oct/2026 | Vision, SDP and MVP scope agreed by the team; SRS and UI prototype baselines in /docs; product backlog created in Jira. |
| PA2 – Requirements & initial design | 01/Nov/2026 | User stories with AC for all MVP epics reviewed by QA; prototype reviewed by PO; architecture and spike results documented. |
| M2 – Lifecycle Architecture (PA3) | 15/Nov/2026 | Architecture documented and validated by v0.1 running end-to-end in Telegram (text → PENDING card → confirm → ledger); Test Plan approved. |
| Beta (PA4) | 29/Nov/2026 | Photo logging, debt simplification, /balance and VietQR settlement work; no open Blocker/Critical bugs; beta used by pilot room(s). |
| M3 – Initial Operational Capability (PA5) | 13/Dec/2026 | All MVP features meet the Definition of Done; full regression passed; release notes and user guide published; final demo delivered. |

Releases

| Release | Date | Type | Content |
| --- | --- | --- | --- |
| UI Prototype | 18/Oct (baseline), 01/Nov/2026 (final) | Prototype / design demo (non-executable) | Chat interaction flows, confirmation card, settlement and reminder messages, Mini App screens. |
| v0.1 | 15/Nov/2026 | Internal demo (PA3) | Text expense logging with currency normalization, PENDING confirmation card, state machine, ledger persistence. |
| v0.5 Beta | 29/Nov/2026 | Beta for pilot room groups (PA4) | Adds receipt/bill OCR and multimodal input, debt simplification, /balance summary, VietQR settlement. |
| v1.0 MVP | 13/Dec/2026 | Final release and demo (PA5) | Adds meter scanner and rent breakdown, polite automated reminders, Telegram Mini App, and beta bug fixes. |

Each release is tagged on the main branch in GitHub (v0.1.0, v0.5.0, v1.0.0) and accompanied by release notes.

Project Schedule

Figure 2. Project timeline (10 weeks, 5 sprints)

Sprint timeline

| Sprint | Phase | Sprint Planning | Backlog refinement | Review, Retro & PA due | Release / milestone |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 | Inception | Mon 05/Oct | Mon 12/Oct | Sun 18/Oct | PA0 (Sun 11/Oct), PA1, M1 |
| Sprint 2 | Elaboration | Mon 19/Oct | Mon 26/Oct | Sun 01/Nov | PA2, final UI prototype |
| Sprint 3 | Elaboration | Mon 02/Nov | Mon 09/Nov | Sun 15/Nov | PA3, v0.1, M2 |
| Sprint 4 | Construction | Mon 16/Nov | Mon 23/Nov | Sun 29/Nov | PA4, v0.5 Beta |
| Sprint 5 | Construction | Mon 30/Nov | Mon 07/Dec | Sun 13/Dec | PA5, v1.0, M3 |

Project Resourcing

Staffing. The team has 5 members for the whole project, each contributing about 10 hours per week. Effort shifts by sprint as shown below; during Sprints 3–5 every member also takes implementation sub-tasks under the Technical Lead's coordination.

| Member | Role | Main focus by sprint |
| --- | --- | --- |
| Kiệt Trịnh Võ Nam | Scrum Master / Project Lead | All sprints: ceremonies, Jira board, plans and status reports. |
| Tôn Huỳnh Chí | Product Owner / BA | S1–S2: interviews, Vision, SRS, user stories. S3–S5: backlog priorities, acceptance reviews, pilot coordination. |
| Hào Nguyễn Gia | Technical Lead | S2–S3: architecture, spikes, infrastructure. S3–S5: implementation, code review, releases. |
| Nam Phạm Hữu | UI/UX Designer | S1–S3: flows, wireframes, prototype, detailed UI. S4–S5: Mini App UI, usability fixes. |
| Hưng Cao Quảng | QA / Tester | S1–S2: requirement reviews. S3: Test Plan. S4–S5: test execution, regression, pilot/UAT. |

Tools and infrastructure (free tiers): Telegram Bot API and Mini App; Google Cloud Vision free quota or Tesseract for OCR; free cloud hosting for the backend; Redis and PostgreSQL free tiers; GitHub, Jira, Slack, Moodle and the class Facebook group.

Project Monitoring and Control

Reporting

Project status is reported through the following channels:

- Daily Scrum (15 minutes, in a call or asynchronously in the group Slack channel): what was done, what is next, and blockers. Items at risk of missing their due date are raised here and explained in a "Reason for Delay" comment on the Jira ticket.

- Sprint Planning (first Monday of each sprint): agree on the sprint goal and backlog; assignees break work into sub-tasks with due dates.

- Sprint Review (end of sprint): demo the increment to the Product Owner, and to the instructor/TAs when the PA requires it.

- Sprint Retrospective (end of sprint): agree on improvements; notes stored in /docs/management.

- Weekly status report by the Scrum Master in /docs/management: progress against plan, burndown, risks and blockers.

- Jira board and burndown chart as the single source of truth for progress; PR links are attached to tickets.

- Slack group channel for day-to-day discussion; Moodle and the class Facebook group for course notices and submissions.

Work items follow the team's Jira SOP:

- Issue types: Epic (one per MVP feature), User Story (with acceptance criteria), Task, Sub-task and Bug.

- Every active Story, Task and Sub-task has a due date; a sub-task's due date cannot exceed its parent's.

- Workflow: To Do → In Progress → In Review → Done. No ticket in progress or in review may be unassigned.

- Definition of Done: code approved and merged; QC verified with no open Blocker/Critical/Major bugs; all sub-tasks done; documentation updated.

Risk Management

Probability is rated from 0.1 (rare) to 0.9 (almost certain) and impact from 1 (negligible) to 10 (critical). Risk exposure = Probability × Impact. Risks are sorted by exposure (priority 1 = highest).

| Risk ID | Risk description | Proba-bility | Impact | Risk exposure | Priority | Mitigation strategy or contingency plan |
| --- | --- | --- | --- | --- | --- | --- |
| R01 | OCR misreads amounts on low-quality or crumpled receipts, bills and meter photos. | 0.7 | 8 | 5.6 | 1 | Compare OCR engines on real receipts in the Sprint 2 spike; preprocess images; always show the extracted amount on the PENDING card with [Edit Amount]; nothing is committed without confirmation. |
| R02 | MVP scope (10 features) is too large for 3 implementation sprints with a part-time team. | 0.6 | 8 | 4.8 | 2 | Strict backlog priority; Medium-priority items (meter scanner, Mini App) are scheduled last and can move to a later release with PO approval; track velocity each sprint. |
| R03 | Member availability drops because of other courses and exams. | 0.6 | 6 | 3.6 | 3 | Mandatory due dates and Daily Scrum early warnings; pair members on critical work for cover; keep buffer in Sprint 5. |
| R04 | Ambiguous Vietnamese chat input (slang, currency tokens, mentions) is parsed incorrectly. | 0.6 | 6 | 3.6 | 4 | Build a test corpus from interviews and pilot chats; default to equal split; confirmation card with edit before commit. |
| R05 | Race conditions when several members send expenses at the same time. | 0.5 | 7 | 3.5 | 5 | Per-group Redis lock (Group_State_Lock, TTL 300 s); concurrency tests in Sprint 3. |
| R06 | Incorrect VietQR payload (bank BIN, amount, CRC) leads to failed or wrong transfers. | 0.3 | 9 | 2.7 | 6 | Follow EMVCo / Napas specification; unit-test payload and CRC; test with several banking apps; debts clear only after [Confirm Received]. |
| R07 | Team lacks experience with FastAPI/Node.js, Redis and Telegram Mini Apps. | 0.5 | 5 | 2.5 | 7 | Technical spikes in Sprint 2; Technical Lead pairing, coding standards and code review. |
| R08 | Free-tier limits (OCR quota, hosting cold starts) disrupt demos or the pilot. | 0.4 | 6 | 2.4 | 8 | Tesseract fallback; monitor quota; warm up services before demos. |
| R09 | Telegram constraints (group privacy mode, webhook limits, Mini App authentication). | 0.4 | 6 | 2.4 | 9 | Validate in the Sprint 2 spike; configure bot permissions; verify Mini App initData on the backend. |
| R10 | Leakage of financial data or bank account details. | 0.3 | 8 | 2.4 | 10 | Store minimal data; keep secrets out of the repository; HTTPS only; restrict access to group members. |
| R11 | Reminders feel intrusive, reducing adoption. | 0.3 | 5 | 1.5 | 11 | Review reminder wording with pilot users; limit reminders to the 24h/48h schedule; allow the room to adjust frequency. |

The Scrum Master reviews this register at every Sprint Planning and Retrospective, updates probabilities and impacts, and records new risks in Jira.

Configuration Management

- Source code and documents: a GitHub repository with the structure required by PA0: /src (bot backend and Mini App); /docs/management, /docs/requirements, /docs/analysis and design, /docs/test; and /pa with one subfolder per PA submission.

- Branching: main (protected; releases only, tagged v0.1.0, v0.5.0, v1.0.0), develop (integration), and short-lived feature/<JIRA-KEY>-description and bugfix/<JIRA-KEY>-description branches.

- Code review: every change is merged through a pull request with at least one approval (peer or Technical Lead); the PR link is attached to the Jira ticket and commit messages start with the Jira issue key.

- Continuous integration: GitHub Actions runs linting and unit tests on every pull request.

- Secrets: bot tokens, database credentials and OCR keys are kept in environment variables / GitHub Secrets and never committed.

- Documents: drafts may be co-edited in Google Drive; approved versions are exported to /docs and versioned in GitHub. UI prototype source files are linked from /docs/analysis and design.

- Backlog and change control: all requirements, tasks, bugs and change requests are tracked in Jira; scope changes require Product Owner approval and are recorded in Jira and the MVP decision record.

- Environments: Local (developers), Testing (QC verification after PR approval) and Demo/Pilot (bot used by pilot rooms and for PA demos).